## Dashboard
Akiko / Being Tea Co. — Roadmap Control Center
Local owner-review tracker. Blank analytics are unknown, never zero. Nothing in this workbook is published or externally scheduled.
Planning input | Value |  | Package control | Current state | Owner gate | State
Start date | 2026-08-09 12:00 |  | Queue records | 30 | V2 master likeness | AWAITING_OWNER
Known follower floor | 4 |  | Ready for owner review | 30 | 30 v2 derivatives | AWAITING_OWNER
Stretch target | 1000000 |  | Owner-approved rows | 0 | 30 captions + alt text | AWAITING_OWNER
Known maximum gap | 999996 |  | Externally scheduled | 0 | Persona / pronouns | AWAITING_OWNER
Inclusive runway (days) | 145 |  | Published records verified | 0 | Profiles / bios | AWAITING_OWNER
Required net / day | 6896.5241 |  | Meta authorization | UNRESOLVED | Analytics baseline | AWAITING_OWNER
Required net / week | 48275.669 |  | X write access | UNVERIFIED | Crisis owner | AWAITING_OWNER
|  |  | MyPersonas setting | Last verified L0 | Separate publish instruction | AWAITING_OWNER
|  |  | Local draft pack | VALID / IMPORT DISABLED
Follows per 1,000 qualified views | Conversion | Qualified views required
1 | 0.1% | 999996000
3 | 0.3% | 333332000
5 | 0.5% | 199999200
10 | 1% | 99999600
Scenario | Implied net followers | Interpretation
Conservative learning | 500–6,000 | Useful positioning data; far below stretch
Strong emerging brand | 15,000–120,000 | Repeatable series and owned-audience potential
Breakout system | 250,000–2,000,000 | Several major winners plus continuing conversion
Decision rule: safety, rights, disclosure, account health, and qualified audience growth outrank raw views. Viral outliers are reported separately from seven- and 28-day medians.

## Weekly Data
Weekly Analytics Input and Reforecast
Yellow columns are owner/platform inputs. ISO weeks are Monday–Sunday; the first week ends on day 8 from the Aug 9 baseline, while Forecast Day 7 is Aug 15.
Week start | Week end | IG open | IG close | FB open | FB close | X open | X close | Combined close | Net followers | Stretch reference | Variance | Qualified views | Attributed follows | Follows / 1,000 | Shares | Saves | Meaningful comments | Profile visits | Negative feedback | Shares / 1,000 | Saves / 1,000 | Comments / 1,000 | Profile visits / 1,000 | Negative / 1,000 | Production hours | Production cost | Email signups | Revenue | Notes
2026-08-10 12:00 | 2026-08-16 12:00 | [8 empty] | 55176
2026-08-17 12:00 | 2026-08-23 12:00 | [8 empty] | 103452
2026-08-24 12:00 | 2026-08-30 12:00 | [8 empty] | 151728
2026-08-31 12:00 | 2026-09-06 12:00 | [8 empty] | 200003
2026-09-07 12:00 | 2026-09-13 12:00 | [8 empty] | 248279
2026-09-14 12:00 | 2026-09-20 12:00 | [8 empty] | 296555
2026-09-21 12:00 | 2026-09-27 12:00 | [8 empty] | 344830
2026-09-28 12:00 | 2026-10-04 12:00 | [8 empty] | 393106
2026-10-05 12:00 | 2026-10-11 12:00 | [8 empty] | 441382
2026-10-12 12:00 | 2026-10-18 12:00 | [8 empty] | 489657
2026-10-19 12:00 | 2026-10-25 12:00 | [8 empty] | 537933
2026-10-26 12:00 | 2026-11-01 12:00 | [8 empty] | 586209
2026-11-02 12:00 | 2026-11-08 12:00 | [8 empty] | 634484
2026-11-09 12:00 | 2026-11-15 12:00 | [8 empty] | 682760
2026-11-16 12:00 | 2026-11-22 12:00 | [8 empty] | 731036
2026-11-23 12:00 | 2026-11-29 12:00 | [8 empty] | 779311
2026-11-30 12:00 | 2026-12-06 12:00 | [8 empty] | 827587
2026-12-07 12:00 | 2026-12-13 12:00 | [8 empty] | 875863
2026-12-14 12:00 | 2026-12-20 12:00 | [8 empty] | 924138
2026-12-21 12:00 | 2026-12-27 12:00 | [8 empty] | 972414
2026-12-28 12:00 | 2026-12-31 12:00 | [8 empty] | 1000000

## Content Queue
30-Post Owner Approval Queue
Every row is local only. Approve / Deny / Revise is a content decision, not permission to schedule or publish.
Record ID | Concept | Platform | Proposed local time | Timezone | Queue status | Owner decision | Image path | Caption location | AI disclosure required | Externally scheduled
AKI-01-IG | 01 | Instagram | 2026-08-10 09:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/01.jpg | APPROVAL-PACK.md#instagram-post-01 | TRUE | FALSE
AKI-01-FB | 01 | Facebook | 2026-08-10 09:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/01.jpg | APPROVAL-PACK.md#facebook-post-01 | TRUE | FALSE
AKI-01-X | 01 | X | 2026-08-10 09:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/01.jpg | APPROVAL-PACK.md#x-post-01 | TRUE | FALSE
AKI-02-IG | 02 | Instagram | 2026-08-10 18:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/02.jpg | APPROVAL-PACK.md#instagram-post-02 | TRUE | FALSE
AKI-02-FB | 02 | Facebook | 2026-08-10 18:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/02.jpg | APPROVAL-PACK.md#facebook-post-02 | TRUE | FALSE
AKI-02-X | 02 | X | 2026-08-10 18:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/02.jpg | APPROVAL-PACK.md#x-post-02 | TRUE | FALSE
AKI-03-IG | 03 | Instagram | 2026-08-11 12:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/03.jpg | APPROVAL-PACK.md#instagram-post-03 | TRUE | FALSE
AKI-03-FB | 03 | Facebook | 2026-08-11 12:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/03.jpg | APPROVAL-PACK.md#facebook-post-03 | TRUE | FALSE
AKI-03-X | 03 | X | 2026-08-11 12:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/03.jpg | APPROVAL-PACK.md#x-post-03 | TRUE | FALSE
AKI-04-IG | 04 | Instagram | 2026-08-12 10:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/04.jpg | APPROVAL-PACK.md#instagram-post-04 | TRUE | FALSE
AKI-04-FB | 04 | Facebook | 2026-08-12 10:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/04.jpg | APPROVAL-PACK.md#facebook-post-04 | TRUE | FALSE
AKI-04-X | 04 | X | 2026-08-12 10:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/04.jpg | APPROVAL-PACK.md#x-post-04 | TRUE | FALSE
AKI-05-IG | 05 | Instagram | 2026-08-12 18:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/05.jpg | APPROVAL-PACK.md#instagram-post-05 | TRUE | FALSE
AKI-05-FB | 05 | Facebook | 2026-08-12 18:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/05.jpg | APPROVAL-PACK.md#facebook-post-05 | TRUE | FALSE
AKI-05-X | 05 | X | 2026-08-12 18:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/05.jpg | APPROVAL-PACK.md#x-post-05 | TRUE | FALSE
AKI-06-IG | 06 | Instagram | 2026-08-13 12:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/06.jpg | APPROVAL-PACK.md#instagram-post-06 | TRUE | FALSE
AKI-06-FB | 06 | Facebook | 2026-08-13 12:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/06.jpg | APPROVAL-PACK.md#facebook-post-06 | TRUE | FALSE
AKI-06-X | 06 | X | 2026-08-13 12:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/06.jpg | APPROVAL-PACK.md#x-post-06 | TRUE | FALSE
AKI-07-IG | 07 | Instagram | 2026-08-14 10:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/07.jpg | APPROVAL-PACK.md#instagram-post-07 | TRUE | FALSE
AKI-07-FB | 07 | Facebook | 2026-08-14 10:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/07.jpg | APPROVAL-PACK.md#facebook-post-07 | TRUE | FALSE
AKI-07-X | 07 | X | 2026-08-14 10:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/07.jpg | APPROVAL-PACK.md#x-post-07 | TRUE | FALSE
AKI-08-IG | 08 | Instagram | 2026-08-15 10:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/08.jpg | APPROVAL-PACK.md#instagram-post-08 | TRUE | FALSE
AKI-08-FB | 08 | Facebook | 2026-08-15 10:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/08.jpg | APPROVAL-PACK.md#facebook-post-08 | TRUE | FALSE
AKI-08-X | 08 | X | 2026-08-15 10:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/08.jpg | APPROVAL-PACK.md#x-post-08 | TRUE | FALSE
AKI-09-IG | 09 | Instagram | 2026-08-15 18:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/09.jpg | APPROVAL-PACK.md#instagram-post-09 | TRUE | FALSE
AKI-09-FB | 09 | Facebook | 2026-08-15 18:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/09.jpg | APPROVAL-PACK.md#facebook-post-09 | TRUE | FALSE
AKI-09-X | 09 | X | 2026-08-15 18:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/09.jpg | APPROVAL-PACK.md#x-post-09 | TRUE | FALSE
AKI-10-IG | 10 | Instagram | 2026-08-16 11:00 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/instagram/10.jpg | APPROVAL-PACK.md#instagram-post-10 | TRUE | FALSE
AKI-10-FB | 10 | Facebook | 2026-08-16 11:15 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/facebook/10.jpg | APPROVAL-PACK.md#facebook-post-10 | TRUE | FALSE
AKI-10-X | 10 | X | 2026-08-16 11:30 | America/Anchorage | READY_FOR_OWNER_REVIEW | PENDING | images-v2/x/10.jpg | APPROVAL-PACK.md#x-post-10 | TRUE | FALSE

## Experiments
Initial Experiment Register
Minimums are operating rules for this launch, not universal benchmarks. No experiment is live before publishing begins.
ID | Hypothesis | Primary variable | Primary metric | Minimum useful sample | Scale rule | Revise rule | Stop rule | Learning if it fails | State
AKI-E01 | A face-led cover converts more qualified viewers into profile visits than a process-led cover. | Cover subject | Profile visits / 1,000 qualified views | One matched pair per platform, then replicate | Two repeatable wins | Hold drops or one guardrail worsens | Two failed replications or trust concern | The lesson/process may be stronger than Akiko's face. | PROPOSED
AKI-E02 | A concrete brewing problem earns more saves than a definition-led hook. | Hook type | Saves / 1,000 qualified views | Three matched pairs | Median win without negative feedback | Promising saves but weak completion | Two failed replications | The audience may prefer foundational vocabulary, or the problem is too generic. | PROPOSED
AKI-E03 | A visible source card increases saving on claim-check posts. | Source card present/absent | Saves / 1,000 qualified views | Two matched pairs | Repeatable lift without completion loss | Lift exists but card is visually dense | No lift after two replications | Trust may be better conveyed in caption/link, or the card is not useful enough to save. | PROPOSED
AKI-E04 | On Facebook, a 220–320 word explanation creates more meaningful discussion than a 90–140 word explanation. | Facebook caption word-count band | Meaningful comments / 1,000 qualified views | Four matched pairs per band | Repeatable median winner | Depth helps but costs too much time | No stable difference | Facebook readers may prefer concise utility, or topic matters more than depth. | PROPOSED
AKI-E05 | A one-line brewing log converts practical utility into owned-audience growth. | Download CTA | Confirmed signups / landing visits | 100 tracked visits or four weeks | Useful signups with low complaints | Conversion exists but completion feedback is weak | No signal or consent/trust issue | The utility, landing page, or timing is insufficient; do not assume email itself is unwanted. | PROPOSED

## Risk Register
Failure-Prevention Register
Global pause means no new publishing, scheduling, automated replies, promotion, or campaign activation while investigation is open.
# | Failure mode | Early warning | Preventive control | Approval | Pause threshold | Recovery
1 | Fake engagement or pods | Unexplained spikes; repetitive comments; wrong geography | No buying/trading engagement; vendor audit | Owner for every growth vendor | Any purchased or organized fake activity | Stop vendor; revoke access; rebuild from organic baseline
2 | Engagement bait or spam | Forced tagging; bulk replies; falling comment quality | Utility CTAs; no follow/unfollow or bulk DMs | Owner for new acquisition mechanics | One deceptive mechanic live | Remove; correct; document rule
3 | Copied or unlicensed media | Copyright notice; unknown source; watermark | Source/license ledger; original exports | Rights check before publish | Any unresolved claim | Pause asset; contact owner; replace
4 | Interchangeable AI content | Face drift; duplicates; falling return behavior | Canon lock; human edit; provenance | Every post at launch | Two inconsistent or near-duplicate posts/week | Pause batch; refresh QA; regenerate selectively
5 | Misleading AI identity | Audience believes Akiko is real; missing labels | Bio and post disclosure; no lived claims | Owner identity approval | One material deceptive claim | Correct visibly; audit profiles/archive
6 | Unsupported health/product claims | Detox/cure language; adverse report | Claim matrix; primary sources; escalation | Owner plus specialist | Any personalized advice or credible safety complaint | Pause topic/product; correct; seek review
7 | Audience mismatch/raw views | Views rise while follows/saves/returns fall | Qualified metrics and series continuation | Owner for pillar changes | Two 7-day periods of worsening quality | Stop format; diagnose source; restore wedge
8 | Brand inconsistency/cultural cosplay | Conflicting canon; costume-first; cultural concern | Voice/visual canon; cultural sourcing | Owner for canon changes | One public contradiction or credible concern | Pause; consult; correct and document
9 | Unsafe automation/duplicates | Wrong account; duplicate ID; unsent audit | Approval queue; idempotency; caps; global pause | No L3 until verified | Any unauthorized external action | Pause; reconcile provider state; incident review
10 | Disclosure failure | Missing label; unclear commission; confusion | Embedded disclosure checklist | Owner and campaign | Any live undisclosed consideration | Pause; correct prominently; notify as required
11 | Burnout | Rushed QA; repeat ideas; rising hours | Weekly cap; reserve; rest option | Owner for cap increase | Two weeks above cap or fatigue error | Reduce cadence; use reserve; reset
12 | Reputation crisis | Coordinated mentions; threats; spreading misquote | Single spokesperson; evidence capture | Owner for crisis replies | Threat, rapid harm, or partner safety issue | Global pause; assess; sourced response; postmortem
13 | Policy/recommendation loss | Account warning; reach collapse; restriction | Weekly account-health checks | Owner for appeals | Any restriction or ineligibility | Pause similar content; official appeal
14 | Single-platform dependence | >80% qualified audience or revenue in one channel | Native multi-platform plus owned audience | Owner for channel retirement | Access/reach loss threatens continuity | Shift reserve; notify owned audience
15 | Privacy/impersonation/compromise | Unknown login; fake account; leaked data | Least privilege; 2FA; privacy ledger | Owner for access/recovery | Any credible compromise or doxxing | Global pause; recover; rotate; warn if needed
16 | Founder/Brother Kāruṇya/persona collision | Unclear speaker; founder history in Akiko's first person; blurred cross-posts | Separate bios, source labels, account map, canon ledger | Owner for stories/collabs | One lived-experience misattribution | Pause; correct attribution; separate profiles and archive

## Forecast
Forecast and Reforecast Reference
Stretch values are diagnostic lines, not promises. Scenario bands are planning sensitivities, not industry benchmarks.
Milestone | Linear date | Stretch total | Meaning
10K | 2026-08-10 12:00 | 10000 | Arrives before sound validation can finish
100K | 2026-08-23 12:00 | 100000 | Requires immediate acceleration
250K | 2026-09-14 12:00 | 250000 | Breakout distribution required
500K | 2026-10-20 12:00 | 500000 | Sustained major winners required
1M | 2026-12-31 12:00 | 1000000 | Stretch reference
Scenario | Qualified views | Follow conversion | Implied net followers
Conservative learning | 0.5M–2M | 1–3 / 1,000 | 500–6,000
Strong emerging brand | 5M–20M | 3–6 / 1,000 | 15,000–120,000
Breakout system | 50M–200M | 5–10 / 1,000 | 250,000–2,000,000
Checkpoint day | Date | Linear stretch total
7 | 2026-08-15 12:00 | 48280
14 | 2026-08-22 12:00 | 96555
28 | 2026-09-05 12:00 | 193107
30 | 2026-09-07 12:00 | 206900
60 | 2026-10-07 12:00 | 413795
90 | 2026-11-06 12:00 | 620691
145 | 2026-12-31 12:00 | 1000000
Weekly reforecast: update verified follower totals, seven- and 28-day medians, qualified views, follows per 1,000, production time, and remaining runway. Classify the stretch as on mathematical line, requires acceleration, or no longer evidence-supported.
Formulas:
Linear date = 'Dashboard'!$B5+[Milestone]-1

## Owner Decisions
Approve / Deny / Revise Queue
Complete this sheet or the matching markdown checklist. Approval does not authorize scheduling or publishing.
ID | Decision | Recommended default | Owner choice | Why it matters | Blocks
D01 | Pronunciation and she/her pronouns | AH-kee-koh; she/her | PENDING | Public consistency | Profile and copy finalization
D02 | Fictional AI host model | Approve with plain disclosure | PENDING | Truth and platform compliance | All launch posts
D03 | V2 master likeness | Approve or give specific revision | PENDING | Identity lock | All derivative approval
D04 | 30 v2 derivatives | Review contact sheet and exceptions | PENDING | Final visual approval | Queue approval
D05 | Concepts 02–10 wardrobe/world | Approve current or request modern-neutral test | PENDING | Cultural and brand framing | Derivative approval
D06 | Public Castleborn connection | Keep private during launch | PENDING | Brand focus and canon control | Bio/lore decisions
D07 | Profile names, bios, and links | Use proposed Being Tea Co. ¦ Akiko system | PENDING | Conversion and disclosure | Account-side profile edits
D08 | Release order and test windows | Preserve order; shift after approval | PENDING | Clean learning sequence | Scheduling
D09 | Comment/DM and crisis owner | Owner review; name global-pause owner | PENDING | Safety and response capacity | Community launch
D10 | Sponsored-content cap | 15% rolling 28 days | PENDING | Trust protection | Commercial policy
D11 | Separate external action | Do not issue until access is fixed | PENDING | Authorization boundary | Any scheduling/publishing

## Sources
Source and Definition Register
Official platform pages are rechecked before upload. Plain URLs are retained for auditability.
Area | Source | URL / file | Use
Instagram | Recommendation eligibility | https://www.facebook.com/help/instagram/653964212890722 | Account health and recommendation checks
Instagram | Account Status | https://www.facebook.com/help/instagram/338481628002750/ | Restriction and removal review
Instagram | Photo dimensions | https://www.facebook.com/help/1631821640426723/ | 1080-wide and supported ratios
Meta | AI-generated content labels | https://about.fb.com/news/2024/04/metas-approach-to-labeling-ai-generated-content-and-manipulated-media/ | Synthetic-media disclosure
Facebook | Original creator priority | https://about.fb.com/news/2026/03/rewarding-original-creators-on-facebook/ | Originality and distribution
Facebook | Account Status | https://www.facebook.com/help/1392616391875085 | Page/account health
X | Posting images | https://help.x.com/en/using-x/posting-gifs-and-pictures | Image formats and limits
X | Authenticity | https://help.x.com/en/rules-and-policies/authenticity | Spam, fake persona, and deception rules
X | Automation | https://help.x.com/en/rules-and-policies/x-automation | Official automation boundaries
Brand | Being Tea Co. | https://beingteaco.com/ | Owner-controlled primary site
Education | Kew tea plant | https://www.kew.org/plants/tea-plant | Camellia sinensis fundamentals
Education | UNESCO tea practices | https://ich.unesco.org/en/RL/traditional-tea-processing-techniques-and-associated-social-practices-in-china-01884 | Cultural attribution
Package | Full roadmap | FULL-ROADMAP-2026-08-09.md | Strategy and stretch math
Package | Measurement system | MEASUREMENT-COMMUNITY-MONETIZATION-RISK-2026-08-09.md | Metric definitions and controls
Package | Approval pack | APPROVAL-PACK.md | Thirty captions, alt text, and decisions